## LES Amendment data
ID | Task | Status | Type of Review | Start | End | Duration (days) | No. Milestones Completed | Total Milestones | Pct Complete
1 | Acceptance | Completed | Safety and Safeguards | 2024-08-29 | 2025-01-10 | 134 | 4 | 4 | 100%
2 | Draft Safety Evaluation Report and Request for Additional Information | In progress | Safety and Safeguards | 2024-11-26 |  | 97 | 0 | 4 | 0%
3 | Issue RAIs and Receive Responses | Pending | Safety and Safeguards | 2025-03-14 |  | 28 | 0 | 4 | 0%
4 | Resolve RAIs | Pending | Safety and Safeguards | 2025-04-11 |  | 14 | 0 | 4 | 0%
5 | Final SE Input | Pending | Safety and Safeguards | 2025-04-28 |  | 4 | 0 | 4 | 0%
6 | Concurrence on Final SE Input | Pending | Safety and Safeguards | 2025-05-05 |  | 18 | 0 | 4 | 0%
7 | Complete SE and Issue Approval | Pending | Safety and Safeguards | 2025-05-30 |  | 0 | 0 | 2 | 0%
1 | ER Acceptance | Completed | Environmental Impact | 2024-09-17 | 2024-11-26 | 70 | 1 | 1 | 100%
2 | Draft EA | In progress | Environmental Impact | 2024-11-26 |  | 108 | 0 | 4 | 0%
3 | Final EA | Pending | Environmental Impact | 2025-04-14 |  | 16 | 0 | 2 | 0%