## Sheet1
This data is updated occasionally - last updated on 03/21/2024.
ID | Task | Status | Type of Review | Start | End | Duration (days) | No. Milestones Completed | Total Milestones | Pct Complete
1 | Application Acceptance | Completed | Safety and Safeguards | 2024-01-04 | 2024-03-01 | 57 | 5 | 5 | 100%
1.1 | Initial Draft SER | Pending | Safety and Safeguards | 2024-03-01 | 2024-08-16 | 168 | 0 | 15 | 0%
1.2 | Issue RAIs | Pending | Safety and Safeguards | 2024-08-19 | 2024-08-30 | 11 | 0 | 15 | 0%
1.3 | Resolve RAIs | Pending | Safety and Safeguards | 2024-09-02 | 2024-09-27 | 25 | 0 | 15 | 0%
1.4 | Final SER Input | Pending | Safety and Safeguards | 2024-10-01 | 2024-10-15 | 14 | 0 | 15 | 0%
1.5 | Concurrence on Final SER Input | Pending | Safety and Safeguards | 2024-10-16 | 2024-10-25 | 9 | 0 | 4 | 0%
1.6 | Complete SER and Issue License | Pending | Safety and Safeguards | 2024-10-28 | 2024-11-08 | 11 | 0 | 2 | 0%
2 | ER Acceptance | Completed | Environmental Impact | 2024-01-04 | 2024-01-25 | 21 | 1 | 1 | 100%
2.1 | Draft EA | Pending | Environmental Impact | 2024-01-25 | 2024-09-13 |  | 0 | 3 | 0%
| State Review of Draft EA | Pending | Environmental Impact | 2024-09-16 | 2024-10-15 | 228 | 0 | 1 | 0%
2.2 | Final EA | Pending | Environmental Impact | 2024-10-16 | 2024-10-31 | 15 | 0 | 2 | 0%

## Sheet2
Completed
In progress
Pending